## Slide 1
TOPIC AREA: PROJECT MECHANICS
FINDING 1: Regularity of communication between data collectors and data personnel results in higher quality data uploads and timeliness of delivery to the central database.
FINDING 2: Use of data entry deadlines increases data upload substantially. These deadlines should be set in the early spring and late fall to avoid field work season.
FINDING 3: Upload of data in initial years of project results in more publications by the team (we believe, need to evaluate relative to other teams although confounded)
RECOMMENDATION 1: Project Leadership’s support of and active role in ensuring timely delivery of project data to the database is important to increase database personnel effectiveness. Database personnel should provide transparency to project leadership and principal investigators as to the status of data delivery by collaborators.

## Slide 2
TOPIC AREA: PERSONNEL
FINDING 4: Database approach and personnel hired are key parameters with differing models of implementation possible. Consideration of project funding, existing infrastructure, use, and
legacy are important (as discussed in JSWC paper).
FINDING 5: Data personnel become indirect enforcers of data upload timelines, quality, follow-through of carrying out protocols, and clarifiers of data protocols, methods, and units.
RECOMMENDATION 2: Personnel tasked with managing the database should have expertise in computer science as well as expertise (or strong working knowledge) in science disciplines involved in the project.

## Slide 3
TOPIC AREA: DATABASE
FINDING 6: Length of period* that exists for data entry by collectors decreases as project ages, with the greatest length of time in Y1 and least in Y5. *difference between time of in-field collection and online entry
FINDING 7: Forced standardization of metadata is important to reduce inconsistencies, gaps, and errors because generally free-form text.
RECOMMENDATION 3: Large multi-institution and multi-disciplinary projects should establish standardized protocols and processes in conjunction with a centralized database to facilitate the research. These need to be operational as quickly as possible to harmonize data collection with data end uses.

## Slide 4
TOPIC AREA: DATABASE MECHANICS
FINDING 8: Data collectors edit data post-entry requiring versioning abilities and transparency to data consumers.
FINDING 9: Having users actually use the entered data speeds up the data quality control process as they will typically quickly find gaps and errors in the entered data.
RECOMMENDATION 4: Data management systems need to support versioning as project data churns due to quality control reviews, synthesis work, and dataset curation.

## Slide 5
TOPIC AREA: PROJECT INFRASTRUCTURE RECOMMENDATIONS
FINDING 10: Large collaborative projects need data management infrastructure to support the science. The challenges facing researchers are that standard University provided tools like centralized storage, identity management, and general software like Microsoft Office do not address the complex needs of managing data for a project. People with computational and communication skills are necessary to build the infrastructure using the University provided tools, but do need not be full time employees (FTE) supported only by the project.
RECOMMENDATION 5: Universities should provide data management resources (software, hardware, and people) to Big Data style research projects. Getting this right equates to advancement of science by the team, refinement and expansion of research questions, and more efficient use of scientist time due to better workflows established.

## Slide 6
DATA MANAGEMENT PERSONNEL
For CSCAP, we have had 2-3 individuals during the life of the project supporting data management, but none were solely tasked with CSCAP data management. For nearly all research projects, there is little chance of hiring three or more FTEs. The following tables identify key strengths needed by roles assigned in the project.

## Slide 7
 | Project Manager | Data Manager | Programmer
Database Schema Design | SOME | SOME | STRONG
People Skills | CRITICAL | STRONG | SOME
Programming | SOME | SOME | CRITICAL
Research Science Discipline Knowledge | STRONG | SOME | SOME
Creativity | STRONG | STRONG | STRONG
TABLE 1: CSCAP Data Management Skillsets
CRITICAL - This skillset is necessary
STRONG - Domain expert in the topic
SOME - Working knowledge

## Slide 8
Project Manager | Data Manager | Programmer
Work with researchers to define characterize sites, collection procedures | Check that sites are following procedures | Develop algorithms to check data against established bounds
Identify data entry needs and interfaces | Build requirements for data entry | Develop the software
Set data entry deadlines | Work with sites to get data entered and review quality | Create reports and dashboards showing status
TABLE 2: CSCAP Data Management Tasks - Simplified version